ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting authority

Regional Development Agency Bačka Ltd Novi Sad, Boulevard Mihajla Pupina 20/II, 21101 Novi Sad, Republic of Serbia

## Country background

Climate change projections for SERBIA region estimate that the mean annual air temperatures will rise by 1.3 degrees in 2040 and 2.4 degrees in 2080 compared to 1985-2005 (ClimateChangePost, 2017), which may have negative impacts on crop yields.

## Current situation in the sector

- - Overview of the Situation in Serbia Relevant to the Proposed Project

- Serbia, like many countries in the Balkans, is increasingly facing the consequences of climate change, including more frequent and intense droughts. The changing climate is causing shifts in precipitation patterns, with longer dry spells and more extreme weather events. These shifts have significant impacts on water availability, agriculture, and energy production, particularly in the southern and eastern regions of the country, which are more susceptible to drought.

- In recent years, Serbia has experienced several droughts that have severely affected agriculture, which is a critical sector of the national economy. The 2017 and 2018 droughts were particularly notable, leading to crop failures, water shortages for irrigation, and reduced agricultural yields. Such events have affected food production and strained water resources, both for public supply and industrial use.

- With climate change projections indicating a decrease in precipitation levels and rising temperatures, Serbia is expected to experience an even more pronounced water scarcity problem in the coming decades. As water resources are critical for agriculture, hydropower generation (which provides a significant portion of the country’s electricity), and urban supply, addressing drought risk and improving water management is an urgent priority.

- The PRIMES project is particularly relevant to Serbia, as it aligns with the national goals of improving climate change adaptation and disaster risk reduction. The project would support Serbia's efforts to enhance resilience in communities through better water management, drought prevention, and risk preparedness.

## Related programmes and other donor activities

This project is in agreement with European and national trends. It will create a collaborative environment where participants included in the project will show the ability to achieve national and international competitiveness of the cross - border region.

# OBJECTIVES& EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

General objective: PRIMES aims to build drought risk-resilient communities through their full engagement and proactive participation in implementing joint prevention strategies and local water management plans.

## Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

- Establish the PRIMES multi-level network in the Adriatic-Ionian region for drought risk reduction and prevention, functioning as a transnational governance system within a coordinated policy and methodology framework, translating PRIMES strategies into local-level adaptation and prevention actions.

- Adopt a shared ICT infrastructure to enhance interaction between institutions and water users (citizens, farmers, schools, families, industries, public institutions, etc.), improve drought warning procedures, and facilitate data exchange. This will raise awareness of climate change risks while promoting preventive measures and voluntary adaptation actions.

- Shift communities from a passive drought risk management approach, which focuses on emergency response, to a proactive one that supports risk prevention through active participation in implementing adaptation measures and actions. The project will enable knowledge dissemination and innovative collaboration at local, regional, national, and transnational levels.

## Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

As described in section 4.2. Specific work.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The PRIMES project is based on several key assumptions that are essential for its success and implementation:

Political Will and Support: It is assumed that the relevant national, regional, and local authorities will provide the necessary support for the implementation of drought risk reduction measures and water management strategies. This includes facilitating the establishment of Local Drought Committees (LDCs) and promoting inter-institutional cooperation.

Active Participation of Local Communities: The project assumes that local communities, including citizens, farmers, industries, and other stakeholders, will actively participate in the project’s activities, including the implementation of water management strategies and adaptation measures to address drought risks.

Availability of Data: The project assumes that the necessary data on water resources, drought conditions, and vulnerabilities will be available or can be collected effectively, enabling the creation of appropriate risk management tools and the implementation of the ICT infrastructure.

Collaborative Effort: It is assumed that all project partners, including local institutions, private entities, and community members, will collaborate effectively to develop and implement the PRIMES guidelines and strategies. This collaboration is crucial for the success of the project, especially in terms of knowledge exchange and capacity building.

Sustainability of Results: The project assumes that the measures implemented will have long-term impacts and that the local communities will continue to use the developed tools and strategies even after the completion of the project. This assumes the creation of strong local ownership and the institutionalization of project outcomes.

Adequate Resources: It is assumed that the financial, technical, and human resources allocated for the project will be sufficient to support its objectives, including the development of the ICT infrastructure and the establishment of the Local Drought Committees.

## Risks

The successful implementation of the PRIMES project depends on identifying and mitigating several risks:

Political and Institutional Instability: There is a risk of political or institutional changes that could affect the continuity of project implementation, especially in terms of the involvement of relevant authorities and the commitment to drought risk reduction measures. Changes in political leadership or priorities could delay decision-making or disrupt project activities.

Limited Local Engagement: A risk exists that local communities and stakeholders may not fully engage in the project, either due to lack of awareness or insufficient motivation. If stakeholders, particularly farmers and industry representatives, do not actively participate, the project’s objectives of fostering local adaptation strategies may not be fully realized.

Data Availability and Quality: The success of the project depends on the availability of accurate and timely data on water resources, drought conditions, and vulnerabilities. There is a risk that data may be incomplete, outdated, or difficult to access, hindering the development of appropriate drought risk management strategies and ICT tools.

Resistance to Change: Some communities or local institutions may be resistant to adopting new technologies or strategies for drought risk management. The introduction of new practices or the implementation of the ICT infrastructure may face opposition, particularly if stakeholders do not perceive immediate benefits or if the tools are complex to use.

Capacity Constraints: While the project includes capacity-building activities, there is a risk that local institutions may not have sufficient human resources or technical expertise to effectively manage and maintain the project’s outputs, such as the ICT platform or the water management plans. This could undermine the long-term sustainability of the project.

Climate Uncertainty: Given the uncertain nature of climate change, there is a risk that the projected scenarios for droughts and water availability may not fully reflect future conditions. This could lead to challenges in designing and implementing drought risk reduction strategies that remain relevant in the face of changing climate conditions.

Financial Sustainability: While the project will provide initial funding and resources, there is a risk that long-term financial sustainability for the continuation of drought management activities and the maintenance of infrastructure may not be guaranteed. Without adequate financing mechanisms or political commitment, the outcomes of the project may not be sustained beyond its lifespan.

These risks will be continuously monitored throughout the project, and mitigation strategies will be put in place to minimize their potential impact.

# SCOPE OF THE WORK

## General

### Description of the assignment

Subject of procurement is procurement of expertise for droughts. Work will be executed throughout the project period, 10 months from conclusion of the Contract. Service provider would be included in preparing the questionnaires for the target group. Additionally, Service provider would be responsible for producing the 5 podcasts, the educational package (with other PPs), and the historical atlas of droughts. Service provider will participate in the development of the capacity building program of the project and will create a report based on the evaluation of the capacity building activities of the LDCs. Service provider will be responsible for participating in the development of the Common Drought Risk Reduction Strategy for Adriatic-Ionian Communities, together with the other PPs. Service provider will be engaged to participate in the preparation of the Report on the Climate/Hazard and Scenario, with other PPs. They will also prepare the Vulnerability and Impact Reports (environmental/social/economical) for the territory of the Republic of Serbia (in accordance with the guidelines for report preparation outlined in the project application). Service provider will create ex-ante and ex-post questionnaires and reports for the Republic of Serbia (they will create the questionnaires which the project team will distribute, and based on the feedback, the experts will create the reports). Service provider will develop a Community Water Management Plan for drought risk reduction and prevention for the Republic of Serbia (following the guidelines from the project application). Service provider will lead 4 workshops in the Republic of Serbia.

### Geographical area to be covered

The Republic of Serbia.

### Target groups

Project stakeholders, government officials, NGOs and other interested parties.

## Specific work

A2.2 PRIMES Digital tool-KIT for making resilient community

The contractor would be included in preparing the questionnaires (as members of the TSB) for the target group. Additionally, the contractor would be responsible for producing the 5 podcasts, the educational package (with other PPs), and the historical atlas of droughts.

Set of tools for measuring community risk perceptions and preparedness will be available in the DGT Platform environment. The tool-kit will beformed by:

-Questionnaires and formats for measuring Community Drought Risk Perception and preparedness;

-Pod-cast with interviews from some experts. Possible issues can be: (i) Climate Trends and water issues: what we need to know?; (ii) Risks /Vulnerability/Hazard/Impacts explanations; (iii) How to reduce responsibly daily water consumptions? (iv) why you are part of the solution for risk reduction? (v) Drought and flood risk: two faces of the same medal.

-Educational package for citizens (Educational Materials, short videos, multimedia product, etc.)

-Historical Atlas of Drought cases. It will be prepared through documentary research dedicated to the retrieval of historical sources on floods/droughts and the creation of a database containing good practices/stories/testimonies.

A2.4 Capacity building and training activities for LDCs

Contractor (as members of the TSB) will participate in the development of the capacity building program of the project and will create a report based on the evaluation of the capacity building activities of the LDCs.

The budget allocated for this activity will be paid to the contractor as a fee for conducting training and workshops (events).

-  Capacity building & LDC Training Program -Operative format composed of: (i) guidelines here the phase of the events will be shortly described in terms of phases contents, objectives, timing and material that must be used; (ii) available material description and utilization; (iii) cluster of “stakeholders” to be reached.

- Capacity building activities evaluation reports - The aim of the evaluation reports is to assess the overall effectiveness of the learning process summing up learning outcomes, tools, procedures, and timing.

A2.5 Launching PRIMES Strategy for drought risk resiliency in Adriatic Region

The Contractor will be responsible for participating in the development of the Common Drought Risk Reduction Strategy for Adriatic-Ionian Communities, together with the other PPs.

- A PRIMES Strategy for Drought-risk-resiliency in AI Region - It is in ENG and develops a common vision for boosting communities resilience within the AI Macroregion, creating the conditions for the implementation of Project activities.

* PRIMES Strategy has 3 important territorial challenges:

- increasing the resilience of Adrion communities by promoting Community Water Management Plans at PPs level, with the aim at contributing to full implementation of the Goal-6-targets SD Agenda 2030 as well as of Directive 2000/60/EC and Directive 2007/60/EC, by following the approach of thinking globally, acting locally;

- creating a smarter and homogeneous model of governance for climate-risk reduction in ADRION contexts, involving local, regional, national stakeholders in a participatory-voluntary approach in order to reach multi-sectorial agreements on concrete adaptation actions to implement;

- promoting active participation of local communities and boosting the dissemination of environmental information related to the issues of risk perception, increasing risk awareness, preparedness and risk forecasting with regard to natural and man-made disasters as foreseen by the EUSAIR strategy.

* The PRIMES Strategy will establish the common vision within which the Pilot Communities should assess their resilient profile, measuring their water footprint and their vulnerabilities and consequently implementing their Community Water Management Plans setting common goals, priorities and possibly connecting adaptation actions at network level in order to maximize the strategy impacts.

* The Strategy will also include a communication section on how to promote definitively the  PRIMES Network at EU and Mediterranean level over and after the project life, with the aim to start cooperating with other relevant and already active initiative and platforms such as Climate Adapt, Covenant of Mayor Initiative, Resilient Cities Campaign and similar project such as SmartRiver [Adrion 1042], DRIDANUBE – Drought Risk in the Danube Region (INTERREG), etc.

A3.1 Defining the Community drought-risk Profile

Contractor will be engaged to participate in the preparation of the Report on the Climate/Hazard and Scenario, with other PPs. They will also prepare the Vulnerability and Impact Reports (environmental/social/economical) for the territory of the Republic of Serbia (in accordance with the guidelines for report preparation outlined in the project application).

Profiling of community drought risk thus involves: (i) Defining of climate /hazard data and possible scenarios ; (ii) Evaluating the Community level of Vulnerability/ Resilience. Basically two important steps of analysis will produced by each pilot community. The first one aimed at collecting all scientific information and historical climate/hazard trend data along a broad range of indicators for measuring and characterizing drought hazard patterns such as: (i) trend in temperatures; (ii) frequency, intensity and geographical coverage of precipitation events; (iii) changes in seasonal distribution of precipitation events; (iv) soil moisture and sediment conditions, groundwater; (v) reservoir and lake levels; (vi) stream flow; (vii) ecosystem conditions; (viii) climate projections. The second step of analysis will aim at measuring the Community Vulnerability and resilience level (as to what is at risk and why). This process entails the identification of direct and immediate consequences of a drought, which include reduced crop yields, livestock losses and groundwater depletion, as well as the tracking of secondary and longer-term impacts, including income and livelihood losses and migration of population. This sub-activity will evaluate a potential impact for each user (or group of users) and subsequently make a comprehensive impact assessment for the whole community. Basically the assessment should cover the economic, environmental, and social impacts. The output of an impact assessment should include the: -identification of affected users (e.g. groups, sectors)

- identification of types of direct drought impacts

- assessment of expected damages caused by drought

- ranking of impacts – identification of prioritizedimpacts

- identification of areas with a potential risk of drought impacts, through risk maps

Aim of the present action is to evaluate, within an integrated drought-risk scenario, the Vulnerability Profile od Community in the Republic of Serbia.

Deliverables:

- Climate /Hazard Report and Scenario for Adrion Region - Climate Scenario/Hazard Report for the Adriatic-Ionian area will be produced including climate data, trend and projection. Contractor will be responsible for local/national data production and elaboration.

- Vulnerability and Impact Reports (environmental/social/economical) - Vulnerability Reports will be produced.

- Community Water Footprint Assessment - The Assessment will include an accounting of both blue and green water resources for each sector (agricolture/industry /public/families/schools/etc.). The report will refer to multi-year averages. This level of detail is sufficient for the purpose of awareness-raising.

A3.2 Assessing and Evaluate the Community Risk Perception&Preparedness

Contractor will create ex-ante and ex-post questionnaires and reports for the Republic of Serbia (they will create the questionnaires which the project team will distribute, and based on the feedback, the contractor will create the reports).

- Evaluation and Community Risk Perception Report (ex-ante) -Format and Methodology will be included in the PRIMES Guidelines developed by Contracting Authority.

- Evaluation and Community Risk Perception Report (ex-post) -Format and Methodology will be included in the PRIMES Guidelines developed by Contracting Authority.

* Phase 1 (ex-ante assessment). The core of this phase is to evaluate the initial awareness of the target groups. Activities will be carried out through five steps: (i) Identification of final criteria and indicators to be used; (ii) Identification of the target groups to be sampled, considering their role in society and their localization; (iii) Construction of specific questionnaires for each target group, based on previously identified indicators; (iv) Distribution of questionnaires; (v) Qualitative and quantitative analysis of results.

* Phase 2 (ex post assessment). This phase is related to the evaluation of the key aspects tackled by the project once the results achieved throughout the project activities. Namely, assessing the real empowerment of the target groups in terms of perception, awareness and effective involvement in drought risk adaptation and reduction activities. The questionnaires will be designed considering criteria and indicators defined in Phase 1: “ex ante assessment”.

* Collected questionnaires of phase 1 and phase 2 will be qualitatively and quantitatively analyzed and compared.

A3.3 Implementing Community Water Management Plans for Drought Risk Reduction and Prevention

Contractor will develop a Community Water Management Plan for drought risk reduction and prevention for the Republic of Serbia (following the guidelines from the project application).

- The Plans should include a specific road-map with a set of concrete and measurable actions/activities to be implemented for improving the drought risk resilience of the entire community.  Effective drought management requires a combination of drought mitigation, preparedness and response actions . For each activity, will be clearly define the “triggers”, who is responsible for the action, varying degrees of intensity and the extenuating and contributing circumstances under which a given measure will enter into force. Risk Reduction/Prevention measures will be grouped in:

-Immediate safety net measures

-Short-term measures.

-Mid-term measures

-Long-term measures

Further the measures can be classified as: "soft" measures (awareness campaign, educational campaign, regulations, innovative water management procedures, etc.) or "hard" measure (infrastructures, investments, water-use conflict resolutions, etc). Basically CWM Plans will be drafted and implemented by following the Standard scheme included in the PRIMES Guidelines produced during the A1.3. Each measure/action will be drafted in a standard format where will be defined at least: (i) Title of the action/measure and related short description; (ii) Target Period; (iii) Stakeholder Responsible; (iv) Beneficiaries Related Planning or Regulations; (v) Expected Results; (vi) Monitoring Indicators; (vii) Possible Barriers; (viii) Possible financial Resources; (ix) Relevant Stakeholders.

- Community Water Management Plans for drought risk reduction and Prevention - Community WM Plans will be implemented by applying the Plan-Format and following the Methodology included in the PRIMES Guidelines.

A3.4 Co-Design Workshops for supporting risk profile assessment and Community Water-Management Plans

Contractor will lead 4 workshops in the Republic of Serbia. The budget for this activity would cover the fees for the trainers.

Contractor will be responsible for the following: preparing the agenda and inviting stakeholders, as well as organizing workshops either online or in-person (in a provided space).

Co-design workshops are tailored on different topic as following:

- 1st workshop organized:  hazard identification;

- 2nd workshop organized: vulnerability assessment and risk perception evaluation;

- 3rd/4rth workshop organized for developing of the Community Water Management Plans.

## Project management

### Responsible body

The Contractor is responsible for all activities regarding the contract.

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority is Legal Representative.

### Facilities to be provided by the contracting authority and/or other parties

N/a

# LOGISTICS AND TIMING

## Location

The Republic of Serbia.

## Start date &period of implementation of tasks

The intended start date is 28 May 2026 and the period of implementation of the contract will be 10 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country,shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Experts

Key experts are not required.

### Support facilities& backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped.In particular itmust ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities.It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract.Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and two copies:

- Interim reports before each interim payment. The report shall contain a sufficiently detailed description of the different options to support an informed decision on service provided. The final report must be provided along with the corresponding invoice

Final report before final payment. The report shall contain a sufficiently detailed description of the different options to support an informed decision on service provided. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract.The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is “Services provided in timely, quality and quantity manor, as required in these Terms of Reference”

## Special requirements

Not applicable

* * *